## Runbook
Cloud Migration Runbook Template
Instructions: This runbook contains a list of sample steps to help you prepare and execute a migration. Modify the sample tasks to fit your migration and add additional tasks as needed. Use the "Notes" column to provide additional information or specific execution instructions. Enter any additional details needed to complete the task. Modify selection values by updating the "Selections" tab.
Current Application: |  | <insert URL> |  |  |  | Project Issue: | <insert URL>
New Cloud Application: |  | <insert URL> |  |  |  | Documentation: | <insert URL>
Prep
Confirm all details of the migration plan and path.
ID | Product | Method | Task | Priority | Dependency | Start | End | Duration (minutes) | Assignee | Status | Notes | Documentation
Ex: 0 | All | All | Update runbook | Recommended | none | 2021-01-01 13:00 | 2021-01-01 13:30 | 30 | Rachel Wright | Done | Modify or add to the sample task list below. | Plan your cloud migration
1 | Jira | All | Complete Atlassian's Jira pre-migration checklist | Mandatory | n/a |  |  | 0 |  | To Do |  | Jira pre-migration checklist
2 | Confluence | All | Complete Atlassian's Confluence pre-migration checklist | Mandatory | n/a |  |  | 0 |  | To Do |  | Confluence pre-migration checklist
3 | Bitbucket | All | Complete Atlassian's Bitbucket pre-migration checklist | Mandatory | n/a |  |  | 0 |  | To Do |  | Plan your Bitbucket Server to cloud migration
4 | All | All | Verify the plan to migrate all needed data | Mandatory | n/a |  |  | 0 |  | To Do
5 | All | All | Verify how to handle apps and app data | Mandatory | n/a |  |  | 0 |  | To Do |  | Atlassian Marketplace apps that are available in cloud with migration paths
6 | All | Site Import | Verify the plan to migrate users and groups | Mandatory | n/a |  |  | 0 |  | To Do |  | Determine your user migration strategy
7 | All | All | Verify how to handle attachments | Recommended | n/a |  |  | 0 |  | To Do |  | How to import only part of a Jira export into Jira Cloud, Importing attachments into JIRA Cloud using CSV External System Importer, Import a Confluence Cloud space
8 | All | All | Verify the plan to handle all other types of data like customizations, connections, integrations, scripts, or other settings | Recommended | n/a |  |  | 0 |  | To Do
9 | All | All | Verify how to handle conflicts (Ex: duplicate settings, keys, users, etc.) | Recommended | n/a |  |  | 0 |  | To Do
10 | All | All | Determine information that requires additional manual set up (Ex: Recreating a webhook, installing a custom user macro, etc.) | Recommended | 2021-01-03 |  |  | 0 |  | To Do
11 | All | All | Determine whether downtime is required | Mandatory | n/a |  |  | 0 |  | To Do
12 | All | All | Install migration tools | Recommended | n/a |  |  | 0 |  | To Do |  | Cloud Migration Assistants
13 | All | All | Run data export stress test | Recommended | n/a |  |  | 0 |  | To Do
14 | All | All | Create test cases | Mandatory | n/a |  |  | 0 |  | To Do |  | Link to test cases
15 | All | All | Assign test cases | Mandatory | 14 |  |  | 0 |  | To Do |  | Link to test cases
16 | All | All | Create a communication plan | Recommended | n/a |  |  | 0 |  | To Do |  | Link to comms plan
17 | All | All | Prepare training materials | Recommended | n/a |  |  | 0 |  | To Do |  | Prep training materials
18 | All | All | Verify rollback plan | Recommended | n/a |  |  | 0 |  | To Do
[7 empty] | Duration | 0
Test
Conduct an initial migration test.
Note: If your test migration goes as planned, you may not need a separate migration phase! You may be able to accelerate your timeline and start using the new cloud application immediately. If this is desired, change the items in this section marked "Optional" to "Mandatory".
ID | Product | Method | Task | Priority | Dependency | Start | End | Duration (minutes) | Assignee | Status | Notes | Documentation
19 | All | All | Verify cloud environment is ready to receive test data | Recommended | n/a |  |  | 0 |  | To Do
20 | All | Cloud Migration Assistant | Complete all but final deploy step in the Cloud Migration Assistant | Recommended | n/a |  |  | 0 |  | To Do |  | Use the Jira Cloud Migration Assistant to migrate, Confluence Cloud Migration Assistant
21 | All | All | Back up everything | Mandatory | n/a |  |  | 0 |  | To Do
22 | All | All | Download backup file and store in safe location | Mandatory | 21 |  |  | 0 |  | To Do
23 | All | All | Prevent configuration changes | Optional | 21 |  |  | 0 |  | To Do
24 | All | All | Delay creating new users and groups | Optional | 21 |  |  | 0 |  | To Do
25 | All | All | Pause user sync jobs | Optional | 21 |  |  | 0 |  | To Do
26 | All | All | Post "test migration started" banner | Optional | n/a |  |  | 0 |  | To Do
27 | All | All | Start a test migration | Mandatory | 26 |  |  | 0 |  | To Do
28 | All | All | Install or migrate apps | Recommended | 27 |  |  | 0 |  | To Do
29 | All | All | Move all data, users, and groups | Recommended | 27 |  |  | 0 |  | To Do
30 | All | All | Move attachments | Recommended | 27 |  |  | 0 |  | To Do |  | Importing attachments into JIRA Cloud using CSV External System Importer, Import a Confluence Cloud space
31 | All | All | Connect or integrate other applications | Recommended | 27 |  |  | 0 |  | To Do
32 | All | All | Update application link URLs | Recommended | 27 |  |  | 0 |  | To Do |  | Use AppLinks to link to Atlassian products
33 | All | Script | Run any needed scripts | Recommended | 27 |  |  | 0 |  | To Do
34 | Confluence | Other | Run Jira Macro Repair | Mandatory | 27 |  |  | 0 |  | To Do
35 | All | All | Check for errors or warnings | Mandatory | 27 |  |  | 0 |  | To Do
36 | All | All | Send "start testing" communication | Recommended | n/a |  |  | 0 |  | To Do
37 | All | All | Conduct user acceptance testing | Mandatory | 36 |  |  | 0 |  | To Do |  | Link to test cases
38 | All | All | Address any issues | Mandatory | 37 |  |  | 0 |  | To Do
39 | All | All | Retry the migration (if needed) | Optional | n/a |  |  | 0 |  | To Do
40 | All | All | Complete the migration test | Recommended | 37 |  |  | 0 |  | To Do
41 | All | All | Make "go/no-go" decision | Mandatory | 37 |  |  | 0 |  | To Do
42 | All | All | Finalize production migration date | Mandatory | n/a |  |  | 0 |  | To Do
43 | All | All | Communicate launch date and plan to stakeholders | Recommended | 42 |  |  | 0 |  | To Do |  | Link to comms plan
45 | All | All | Communicate launch date and plan to internal support teams | Recommended | 42 |  |  | 0 |  | To Do |  | Link to comms plan
46 | All | All | Communicate launch date and plan to end users | Recommended | 42 |  |  | 0 |  | To Do |  | Link to comms plan
47 | All | All | Post "migration scheduled" banner | Recommended | 42 |  |  | 0 |  | To Do
[7 empty] | Duration | 0
Migrate
Complete the final migration steps.
ID | Product | Method | Task | Priority | Dependency | Start | End | Duration (minutes) | Assignee | Status | Notes | Documentation
48 | All | All | Prevent configuration changes | Mandatory | n/a |  |  | 0 |  | To Do
49 | All | All | Delay creating new users and groups | Mandatory | n/a |  |  | 0 |  | To Do
50 | All | All | Pause user sync jobs | Mandatory | n/a |  |  | 0 |  | To Do
52 | All | All | Post "migration started" banner | Recommended | n/a |  |  | 0 |  | To Do
53 | All | Cloud Migration Assistant | Complete all but final deploy step in the Cloud Migration Assistant | Recommended | n/a |  |  | 0 |  | To Do |  | Use the Jira Cloud Migration Assistant to migrate, Confluence Cloud Migration Assistant
54 | All | All | Back up everything (again) | Mandatory | n/a |  |  | 0 |  | To Do
55 | All | All | Download backup file and store in safe location | Mandatory | 54 |  |  | 0 |  | To Do
56 | All | All | Start the final migration | Mandatory | n/a |  |  | 0 |  | To Do
57 | All | All | Install or migrate apps | Recommended | 56 |  |  | 0 |  | To Do
58 | All | All | Move all data, users, and groups | Recommended | 56 |  |  | 0 |  | To Do
59 | All | All | Move attachments | Recommended | 56 |  |  | 0 |  | To Do |  | Importing attachments into JIRA Cloud using CSV External System Importer, Import a Confluence Cloud space
60 | All | All | Connect or integrate other applications | Recommended | 56 |  |  | 0 |  | To Do
61 | All | All | Update application link URLs | Recommended | 56 |  |  | 0 |  | To Do |  | Use AppLinks to link to Atlassian products
62 | All | Script | Run any needed scripts | Recommended | 56 |  |  | 0 |  | To Do
63 | Confluence | Other | Run Jira Macro Repair | Mandatory | 56 |  |  | 0 |  | To Do
64 | All | All | Check for errors or warnings | Mandatory | 56 |  |  | 0 |  | To Do
65 | All | All | Verify anonymous access settings | Mandatory | n/a |  |  | 0 |  | To Do |  | Check your anonymous access settings
66 | Jira | Site Import | Update projects with project avatars | Recommended | n/a |  |  | 0 |  | To Do |  | Custom avatars missing after upgrade or migration of Jira server
67 | All | All | Send "start testing" communication | Recommended | n/a |  |  | 0 |  | To Do
68 | All | All | Conduct user acceptance testing | Mandatory | 67 |  |  | 0 |  | To Do |  | Link to test cases
69 | All | All | Address any issues | Mandatory | 68 |  |  | 0 |  | To Do
70 | All | All | Complete the migration | Mandatory | 67 |  |  | 0 |  | To Do
71 | All | All | Make "go/no-go" decision | Mandatory | 67 |  |  | 0 |  | To Do
72 | All | All | Rollback (if needed) | Optional | 67 |  |  | 0 |  | To Do
73 | All | All | Send "migration complete" communication | Recommended | 70 |  |  | 0 |  | To Do |  | Link to comms plan
74 | All | All | Post "migration complete" banner | Recommended | 70 |  |  | 0 |  | To Do
75 | All | All | Decommission previous application | Mandatory | 70 |  |  | 0 |  | To Do
76 | All | All | Complete retrospective | Recommended | n/a |  |  | 0 |  | To Do
77 | All | All | Thank upgrade team | Recommended | n/a |  |  | 0 |  | To Do
78 | All | All | Mark project complete | Recommended | n/a |  |  | 0 |  | To Do
[7 empty] | Duration | 0
Rollback
Undo the migration, if necessary.
79 | All | All | Allow configuration changes | Recommended | n/a |  |  | 0 |  | To Do
80 | All | All | Restart creating new users and groups | Recommended | n/a |  |  | 0 |  | To Do
81 | All | All | Restart user sync jobs | Recommended | n/a |  |  | 0 |  | To Do
82 | All | All | Send "migration stopped" communication | Recommended | n/a |  |  | 0 |  | To Do |  | Link to comms plan
83 | All | All | Post "migration stopped" banner | Recommended | n/a |  |  | 0 |  | To Do |  | LInk to comms plan
84 | All | All | Remove partially migrated data | Optional | n/a |  |  | 0 |  | To Do |  | Reset and delete all data from your cloud site
[7 empty] | Duration | 0
[7 empty] | Total Duration | 0

## Selections
Selections
Instructions: This tab is used to control the available selections in the "Runbook" tab. Add or remove values as needed.
Products
Jira
Confluence
Bitbucket
All
Methods
Cloud Migration Assistant
Site Import
CSV
XML
Third-party App
Script
Other
All
Priority
Recommended
Mandatory
Optional
High
Medium
Low
Status
To Do
In Progress
Done
On Hold